{"text_format":"2","workbook":"xlsx","n_sheets":1,"sheets":["平台工作计划"],"not_rendered":{"charts":0,"images":0,"macros":0,"external_links":0,"defined_names":0,"comments":1,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"run_cost":"one","rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"平台工作计划","index":0,"n_rows":76,"n_cols":101,"rows_kept":76,"cut":false,"hidden":false,"merged":[[0,1,0,9],[0,10,0,16],[0,17,0,23],[0,24,0,30],[0,31,0,37],[0,38,0,44],[0,45,0,51],[0,52,0,58],[0,59,0,65],[0,66,0,72],[0,73,0,79],[0,80,0,86],[0,87,0,93],[0,94,0,100],[2,0,2,9],[8,0,8,9],[31,0,31,9],[44,0,44,9],[68,0,68,9],[74,0,74,9],[4,0,7,0],[9,0,11,0],[12,0,15,0],[16,0,25,0],[26,0,29,0],[32,0,37,0],[38,0,43,0],[45,0,49,0],[50,0,55,0],[56,0,66,0],[69,0,70,0],[71,0,72,0],[4,1,7,1],[9,1,11,1],[12,1,15,1],[16,1,25,1],[26,1,29,1],[32,1,37,1],[38,1,43,1],[45,1,49,1],[50,1,55,1],[56,1,66,1],[69,1,70,1],[71,1,72,1]]}
[null,"■ 园区平台工作计划",{"$nulls":8},"第1周",{"$nulls":6},"第2周",{"$nulls":6},"第3周",{"$nulls":6},"第4周",{"$nulls":6},"第5周",{"$nulls":6},"第6周",{"$nulls":6},"第7周",{"$nulls":6},"第8周",{"$nulls":6},"第9周",{"$nulls":6},"第10周",{"$nulls":6},"第11周",{"$nulls":6},"第12周",{"$nulls":6},"第13周"]
["序号","任务","工作步骤","计划开始日期","计划结束日期","时长(天）","产出物","里程碑","依赖项","完成情况","2025-11-03","2025-11-04","2025-11-05","2025-11-06","2025-11-07","2025-11-08","2025-11-09","2025-11-10","2025-11-11","2025-11-12","2025-11-13","2025-11-14","2025-11-15","2025-11-16","2025-11-17","2025-11-18","2025-11-19","2025-11-20","2025-11-21","2025-11-22","2025-11-23","2025-11-24","2025-11-25","2025-11-26","2025-11-27","2025-11-28","2025-11-29","2025-11-30","2025-12-01","2025-12-02","2025-12-03","2025-12-04","2025-12-05","2025-12-06","2025-12-07","2025-12-08","2025-12-09","2025-12-10","2025-12-11","2025-12-12","2025-12-13","2025-12-14","2025-12-15","2025-12-16","2025-12-17","2025-12-18","2025-12-19","2025-12-20","2025-12-21","2025-12-22","2025-12-23","2025-12-24","2025-12-25","2025-12-26","2025-12-27","2025-12-28","2025-12-29","2025-12-30","2025-12-31","2026-01-01","2026-01-02","2026-01-03","2026-01-04","2026-01-05","2026-01-06","2026-01-07","2026-01-08","2026-01-09","2026-01-10","2026-01-11","2026-01-12","2026-01-13","2026-01-14","2026-01-15","2026-01-16","2026-01-17","2026-01-18","2026-01-19","2026-01-20","2026-01-21","2026-01-22","2026-01-23","2026-01-24","2026-01-25","2026-01-26","2026-01-27","2026-01-28","2026-01-29","2026-01-30","2026-01-31","2026-02-01"]
["Phase.1 标准版开发环境部署"]
[1,"1.1标准版开发环境部署工作","略","2025-11-03","2025-11-03",1,null,"★开发环境部署",null,"已完成"]
[2,"1.2标准版开发环境系统运行数据准备","1.2.1园区组织机构数据初始化","2025-11-04","2025-11-06",3]
[null,null,"1.2.2企业组织机构数据初始化","2025-11-04","2025-11-06",3]
[null,null,"1.2.3地图支撑服务配置","2025-11-04","2025-11-06",3]
[null,null,"1.2.4用户权限配置","2025-11-04","2025-11-06",3,null,"★以开发环境迎接省厅检查"]
["Phase.2 标准版生产环境实施部署"]
[3,"2.1标准版生产环境系统部署","2.1.1部署环境准备包括不限于服务器和网络环境","2025-11-07","2025-11-11",5]
[null,null,"2.1.2标准版程序包准备（含模型应用）","2025-11-11","2025-11-15",5,"标准版部署程序包"]
[null,null,"2.1.3完成标准版程序在生产环境的部署工作","2025-11-15","2025-11-16",2,null,"★标准版部署","2.1.1"]
[4,"2.2标准版生产环境系统运行数据准备","2.2.1园区组织机构数据初始化","2025-11-16","2025-11-17",2]
[null,null,"2.2.2企业组织机构数据初始化","2025-11-16","2025-11-17",2]
[null,null,"2.2.3地图支撑服务配置","2025-11-16","2025-11-20",5]
[null,null,"2.2.4用户权限配置","2025-11-17","2025-11-20",4]
[5,"2.3标准版系统动态数据对接","2.3.1危化品重大危险源企业物联网传感器数据对接（温度，液位，压力，气体）","2025-11-18","2025-12-15",28]
[null,null,"2.3.2管廊、重点区域气体监测系统数据对接。","2025-11-18","2025-12-15",28]
[null,null,"2.3.3车辆、人员定位数据对接（定位卡）","2025-11-18","2025-12-15",28]
[null,null,"2.3.4访客系统（门禁，卡口）数据对接（含一键开闸功能）","2025-11-18","2025-12-15",28]
[null,null,"2.3.5企业双预防系统数据对接","2025-11-18","2025-12-15",28]
[null,null,"2.3.6企业特殊作业系统数据对接","2025-11-18","2025-12-15",28]
[null,null,"2.3.7危险化学品停车场系统数据对接","2025-11-18","2025-12-15",28]
[null,null,"2.3.8企业人员定位系统数据对接","2025-11-18","2025-12-15",28]
[null,null,"2.3.9园区（含高空瞭望，管廊监控）和企业视频数据对接，视频分析数据对接","2025-11-18","2025-12-15",28]
[null,null,"2.3.10短信平台对接联调","2025-11-18","2025-12-15",28]
[6,"2.4标准版系统UAT","2.4.1针对关键用户做部署系统关键用户培训","2025-11-25","2025-11-27",3,null,"★标准版关键用户培训",2.2]
[null,null,"2.4.2园区和企业基础数据在系统中填报","2025-11-26","2025-11-30",5]
[null,null,"2.4.3填报数据稽查检查","2025-11-27","2025-12-02",6,"数据质量问题报告"]
[null,null,"2.4.4系统问题修改及功能优化（敏捷迭代）","2025-11-18","2025-12-15",28,null,null,2.3]
[7,"2.5标准版上线运行","2.5.1标准版上线运行","2025-12-15","2025-12-15",1,null,"★标准版上线运行"]
["Phase.3定制功能业务设计 "]
[7,"3.1需求沟通与调研","3.1.1危废管理模块","2025-11-10","2025-11-14",5]
[null,null,"3.1.2危化品停车场管理模块","2025-11-10","2025-11-14",5]
[null,null,"3.1.3易燃易爆有毒有害气体监测模块","2025-11-10","2025-11-14",5]
[null,null,"3.1.4公共管廊监控预警模块","2025-11-10","2025-11-14",5]
[null,null,"3.1.5公共管廊智能巡检模块（含APP）","2025-11-10","2025-11-14",5]
[null,null,"3.1.6封闭化管理模块升级（含小程序）","2025-11-10","2025-11-14",5]
[8,"3.2需求规格设计（界面原型）","3.2.1危废管理模块","2025-11-15","2025-12-01",16,"软件系统高保真原型",null,"3.1.1"]
[null,null,"3.2.2危化品停车场管理模块","2025-11-15","2025-12-01",16,"软件系统高保真原型",null,"3.1.2"]
[null,null,"3.2.3易燃易爆有毒有害气体监测模块","2025-11-15","2025-12-01",16,"软件系统高保真原型",null,"3.1.3"]
[null,null,"3.2.4公共管廊监控预警模块","2025-11-15","2025-12-01",16,"软件系统高保真原型",null,"3.1.4"]
[null,null,"3.2.5公共管廊智能巡检模块（含APP）","2025-11-15","2025-12-01",16,"软件系统高保真原型",null,"3.1.5"]
[null,null,"3.2.6封闭化管理模块升级（含小程序）","2025-11-15","2025-12-01",16,"软件系统高保真原型",null,"3.1.6"]
["Phase.4定制功能开发测试 "]
[9,"4.1项目详细设计及数据库设计","4.1.1项目详细设计编制","2025-12-02","2025-12-06",5,null,null,3.2]
[null,null,"4.1.2项目详细设计评审","2025-12-07","2025-12-07",1]
[null,null,"4.1.3项目数据库设计编制","2025-12-08","2025-12-13",6]
[null,null,"4.1.4项目数据库设计评审","2025-12-13","2025-12-13",1]
[null,null,"4.1.5项目软件开发计划编制（明确优先级）","2025-12-14","2025-12-14",1,null,"★定制开发计划","4.1.4"]
[10,"4.2程序开发及单元测试","4.2.1危废管理模块","2025-12-15","2026-01-15",30,null,null,"4.1.5"]
[null,null,"4.2.2危化品停车场管理模块","2025-12-15","2026-01-15",30]
[null,null,"4.2.3易燃易爆有毒有害气体监测模块","2025-12-15","2026-01-15",30]
[null,null,"4.2.4公共管廊监控预警模块","2025-12-15","2026-01-15",30]
[null,null,"4.2.5公共管廊智能巡检模块（含APP）","2025-12-15","2026-01-15",30]
[null,null,"4.2.6封闭化管理模块升级（含小程序）","2025-12-15","2026-01-15",30]
[11,"4.3接口开发及测试","4.3.1与应用支撑平台数据交换接口开发","2025-12-20","2026-01-15",27]
[null,null,"4.3.2地图服务对接（含矢量图和倾斜摄影图层）","2025-12-20","2026-01-15",27]
[null,null,"4.3.3易燃易爆、公共管廊气体监测物联网传感器全部数据对接（温度，液位，压力，气体）","2025-12-20","2026-01-15",27]
[null,null,"4.3.4公共管廊视频分析数据对接","2025-12-20","2026-01-15",27]
[null,null,"4.3.5危化品停车场数据对接","2025-12-20","2026-01-15",27]
[null,null,"4.3.6访客系统（门禁，卡口）全部数据对接联调和连续性检查","2025-12-20","2026-01-15",27]
[null,null,"4.3.7可视化指挥系统对接","2025-12-20","2026-01-15",27]
[null,null,"4.3.8园区三维倾斜摄影集成","2025-12-20","2026-01-15",27]
[null,null,"4.3.9能源港卡口小程序数据对接（易帕克）","2025-12-20","2026-01-15",27]
[null,null,"4.3.10微信小程序发布","2026-01-15","2026-01-17",3]
[null,null,"4.3.11接口联调测试","2025-12-20","2026-01-15",27,"测试报告"]
[12,"4.4集成测试","4.4.1软、硬件集成测试","2025-12-20","2026-01-15",27,"测试报告","★集成测试"]
["Phase.5 定制化功能上线"]
[13,"5.1实施部署准备","5.1.1定制化软件系统运行时环境搭建","2026-01-15","2026-01-16",2]
[null,null,"5.1.2定制化软件系统实施部署","2026-01-17","2026-01-19",3]
[14,"5.2UAT测试","5.2.1定制化软件UAT培训","2026-01-20","2026-01-22",3,null,"★定制开发软件用户培训","5.1.2"]
[null,null,"5.2.2园区、企业关键用户试用","2026-01-21","2026-01-23",3]
[15,"5.3平台上线","5.3.1定制化软件上线运行","2026-01-23","2026-01-25",3,null,"★交付平台软件上线"]
["Phase.6 平台验收"]
[16,"6.1软件平台验收","6.1.1软件平台验收","2026-01-26","2026-01-28",3]